## project
Project Planner
[6 empty] | Period Highlight: |  |  |  |  | 14 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS |  |  |  |  | 17 |  |  |  | 21 Days (Including Weekends)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Game States - S | 1 | 3 | 1 | 1 | 85%
Camera - S | 7 | 4 | 2 | 0 | 0%
Texture Class - All | 12 | 5 | 0 | 0 | 0%
Time Class - R | 1 | 1 | 1 | 1 | 100%
Buyer Class - R | 1 | 3 | 0 | 0 | 0%
Weather Class - R | 7 | 3 | 0 | 0 | 0%
User Interface - YT | 10 | 3 | 2 | 2 | 10%
Money Class - YT | 1 | 3 | 1 | 1 | 100%
Location Class - A | 3 | 5 | 2 | 0 | 0%
Entity Class - A | 1 | 2 | 1 | 1 | 95%
Sound - A | 11 | 3 | 0 | 0 | 0%
Win / Lose Conidtion - A | 9 | 2 | 0 | 0 | 0%
Save and Load - WQ | 7 | 3 | 0 | 0 | 0%
Forecast Class - WQ | 1 | 3 | 1 | 2 | 60%
Good to Have:
Negotiation | 0 |  | 0 | 0 | 0%
Speech Bubble generation | 0 |  | 0 | 0 | 0%
Competitor AI | 0 |  | 0 | 0 | 0%
Customer Loss rate | 0 |  | 0 | 0 | 0%
Multiple Weathers | 0 |  | 0 | 0 | 0%
Customer Path finding | 0 |  | 0 | 0 | 0%
Encryption | 0 |  | 0 | 0 | 0%
LUA | 0 |  | 0 | 0 | 0%
Buying During Game | 0 |  | 0 | 0 | 0%